{"text_format":"5","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"props":{"creator":"Kenneth Hurst","last_modified_by":"John  Rundle","company":"Jet Propulsion Laboratory"},"read":"whole","wrapped":"gz","date_system":"1904","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":98,"n_cols":16,"rows_kept":98,"flags":["formulas_cached_only"]}
[{"$nulls":3},"due","$k orig","$k task","$k inst","Hawaii","20% cut","JPL","UC","Brown","Indiana","UCI","USC"]
["Administration",{"$nulls":4},399]
["A","Software engineering plan completed",null,"2001-12-30",104,{"$nulls":3},84]
[{"$nulls":9},19,15,15,15,5,15]
["B","First Annual Report delivered ","JPL","2003-01-30",120,{"$nulls":3},50,50]
["C","Second Annual Report delivered","JPL","2004-01-30",120,{"$nulls":3},50,50]
["D","Final Report delivered","JPL","2004-08-30",55,{"$nulls":3},35,35]
["Code Improvement",{"$nulls":4},931]
[null,"Develop requirements ",null,"2002-02-28",{"$nulls":4},80]
[{"$nulls":9},15,15,15,15,5,15]
["E","Code baseline completed",null,"2002-01-30",206,null,null,0,165]
["VC1","   Simulations: VC Benchmarking, MPI port","UC",{"$nulls":3},35,{"$nulls":3},20]
["VC2","   Visualization: Conversion of IDL to XML ","UC",{"$nulls":3},15,{"$nulls":3},10]
["VC4","   Documentation: ","UC",{"$nulls":3},10,{"$nulls":3},10]
["TT1","   Benchmark single fault MPI code on SAF@Parkfield","Brown",{"$nulls":3},102,{"$nulls":4},75]
[null,"   Baseline parallel HMM","JPL",{"$nulls":3},22,null,null,30]
[null,"   Baseline 3D FEM on Northridge","JPL",{"$nulls":3},22,null,null,0]
[null,"   Single fault MPI code on SAF@Parkfield","JPL",{"$nulls":6},20]
["F","First code improvement completed",null,"2002-06-30",305,null,null,0,213]
["VC5","   Simulations: integrate with Gateway Portal","UC",{"$nulls":3},20,{"$nulls":3},15]
["VC6","   Data Mining: Conversion of KLE, integrate HMM","UC",{"$nulls":3},20,{"$nulls":3},20]
["VC7","   Data Assimilation","UC",{"$nulls":3},10,{"$nulls":3},10]
["VC9","   Documentation","UC",{"$nulls":3},5,{"$nulls":3},3]
["TT2","   Run Parkfield with <=500m cells","Brown",{"$nulls":3},107,{"$nulls":4},95]
[null,"   Run Parkfield with <=500m cells","JPL",{"$nulls":6},10]
[null,"   Automatic parellel mesh refinement","JPL",{"$nulls":3},70,null,null,0]
[null,"   Automatic determination of number of classes","JPL",{"$nulls":3},40,null,null,35]
[null,"   Test using seismic records, and GPS data","JPL",{"$nulls":3},33,null,null,25]
["G","Second code improvement completed",null,"2003-06-30",420,null,null,0,235]
["VC10","   Simulations","UC",{"$nulls":3},30,{"$nulls":3},30]
["VC11","   Data Mining","UC",{"$nulls":3},30,{"$nulls":3},30]
["VC12","   Data Assimilation","UC",{"$nulls":3},10,{"$nulls":3},10]
["VC14","   Documentation","UC",{"$nulls":3},10,{"$nulls":3},5]
["TT3","   Multiple faults","Brown",{"$nulls":3},112,{"$nulls":4},100]
[null,"   Multiple faults","JPL",{"$nulls":6},10]
[null,"   Ingest fault database into FEM","JPL",{"$nulls":3},128,null,null,0]
[null,"   Use RIVA and ParVox for visualiztion of FEM, HMM","JPL",{"$nulls":3},100,null,null,50]
["Interoperability",{"$nulls":4},1220]
["H","Design policy for interoperability agreed upon",null,"2002-06-30",290,null,null,0,275]
["VC3","  API Standardization: Prototype defined","UC",{"$nulls":3},10,{"$nulls":3},10]
["GF1","   Prototype Object Grid Services 1st demo","Ind",{"$nulls":3},180,{"$nulls":5},180]
[null,"  Prototype Object Grid Services 1st demo","JPL",{"$nulls":3},100,null,null,85]
["I","Interoperability prototype tested",null,"2003-06-30",430,null,null,0,340]
["VC8","  API Standardization:Prototype demonstrated","UC",{"$nulls":3},10,{"$nulls":3},10]
["GF2","  Prototype Object Grid Services 2nd demo","Ind",{"$nulls":3},260,{"$nulls":5},220]
[null,"  Prototype Object Grid Services 2nd demo","JPL",{"$nulls":3},150,null,null,100]
[null,"  Prototype Object Grid Services 2nd demo","UCI",{"$nulls":3},5,{"$nulls":6},5]
[null,"  Prototype Object Grid Services 2nd demo","Brown",{"$nulls":3},5,{"$nulls":4},5]
["J","Full interoperability demonstrated",null,"2004-06-30",320,null,null,0,180]
["VC13","  API Standardization: Done","UC",{"$nulls":3},10,{"$nulls":3},10]
[null,"  Object Grid Services operational","Ind",{"$nulls":3},50,{"$nulls":5},60]
[null,"  Object Grid Services operational","JPL",{"$nulls":3},250,null,null,100]
[null,"  Object Grid Services operational","UCI",{"$nulls":3},5,{"$nulls":6},5]
[null,"  Object Grid Services operational","Brown",{"$nulls":3},5,{"$nulls":4},5]
["K","Customer delivery accomplished",null,"2003-11-30",95,null,null,5,50]
[null,null,"Ind",{"$nulls":3},30,{"$nulls":5},20]
[null,null,"JPL",{"$nulls":3},60,null,null,30]
["L","Grid Software wizards completed",null,"2003-11-30",85,null,null,0,55]
[null,null,"Ind",{"$nulls":3},17,{"$nulls":5},15]
[null,null,"JPL",{"$nulls":3},68,null,null,40]
["Education and Outreach",{"$nulls":4},135,null,null,20]
["M","Partnerships formed","JPL/CIT","2002-01-30",30,{"$nulls":4},5]
["N","Educational tools completed","JPL/CIT","2002-11-30",55,{"$nulls":4},5]
["O","Disaster tools developed & transferred","JPL/CIT","2002-11-30",50,{"$nulls":4},10]
["Visualization",{"$nulls":4},0,null,null,10]
[null,"Generate requirements","JPL",{"$nulls":6},10]
["P","Modify RIVA and ParVox for EQ visualiz.",null,"2003-01-30",0]
["Q","Interface RIVA and ParVox",null,"2003-06-30",0]
["R","Demonstrate interoperability",null,"2003-06-30",0]
["Fault database",{"$nulls":4},189,null,null,125]
["S","Design Fault database",null,"2002-06-30",35]
[null,null,"UCI",{"$nulls":3},20,{"$nulls":6},10]
[null,null,"JPL",{"$nulls":3},10,null,null,10]
[null,null,"Ind",{"$nulls":3},5,{"$nulls":5},5]
["T","Preliminary fault database","UCI","2002-12-31",42,{"$nulls":8},30]
["U","Functional fault data base","UCI","2003-06-30",25,{"$nulls":8},20]
["V","Updated fault database","UCI","2003-12-31",42,{"$nulls":8},35]
["W","Publish Fault base documentation","UCI","2004-12-31",45,{"$nulls":8},15]
["Federated DB",{"$nulls":4},167,null,null,193]
["X","Select, obtain, and deploy commercial DB","USC","2002-03-01",50,{"$nulls":9},35]
["X1","Buy database system","USC","2002-03-01",null,40,{"$nulls":8},35]
["Y","Design new DB for dynamically defined faults","USC","2002-06-30",40,{"$nulls":9},35]
["Z","Implement key DB","USC","2003-01-30",30,{"$nulls":9},30]
["AA","Define, obtain, develop XML interfaces","USC","2002-11-30",20,{"$nulls":9},15]
["BB","Develop & deploy mechanism for multi-db mining","USC","2003-06-30",27,{"$nulls":9},28]
[null,"Install DB ","JPL","2002-03-01",{"$nulls":5},15]
["Total",{"$nulls":3},"total",3081,null,"2700*0.8=",2160]
[{"$nulls":4},"over/under",-381]
[]
[{"$nulls":7},"total",2160,759,223,310,530,130,208,2160]
[{"$nulls":7},"over/under",0]
[]
[]
[{"$nulls":8},"2002-06-30",967]
[{"$nulls":8},"2003-06-30",733]
[{"$nulls":8},"2004-06-30",410]
[{"$nulls":8},"2004-08-30",50]
[{"$nulls":8},"check sum",2160]

{"sheet":"Sheet2","index":1,"n_rows":24,"n_cols":3,"rows_kept":24,"flags":["formulas_cached_only"]}
[null,"Visualization"]
[null,"ParVox: Provide an interactive volumetric visualization tool to permit user-controlled view from arbitrary vantage points inside a volume, displaying 3D structure, strain, physical properties, meshes, and seismicity through the grid framework.","2004-01-30"]
[null,"Riva: Produce movies of the strain, stress, and displacement  data generated from Virtual California of 1 km resolution for S. California in an integrated way through the grid framework.","2003-06-30"]
[]
[null,"Interoperability"]
["H","Review board approves requirements and a preliminary design for functionality.","2002-06-30"]
[null,"   Graphical user interface"]
[null,"   Requirements and preliminary design published on web."]
["I","Review board approves demonstration of interface of gateway and PARK with simple visualization satisfying preliminary design requirements","2002-11-30"]
["J","Review board approves delivery of completed framework and disloc, simplex, VC, HMM, VISCO, PDPCI, KL mining, PARK, d (17 codes) + SLIDER And updated documentation","2004-06-30"]
[]
[]
["K","Demonstrate integration of one external user application into the framework using the GRID framework wizards","2004-06-30"]
[]
["L","Issue testable 5 year earthquake forecast for M>5 for S California"]
[]
[null,"Code Improvement"]
[]
["E","Code baselines completed for PARK, VC, SLIDER, HMM, (scaling curves for codes which are already parallel)","2002-01-30"]
[]
["F","First code improvement (PARK for 100 m resolution) NEED TIME CONSTRAINT ?x  - establish scaling","2002-06-30"]
[]
[]
["G","VISCO, SIMPLEX,  etc get ressolution & time constraints) spread over F & G","2003-06-30"]

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}