{"text_format":"5","workbook":"xls","n_sheets":1,"sheets":["Sheet1"],"props":{"last_modified_by":"Andrea Donnellan"},"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","wrapped":"gz","date_system":"1904","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":23,"n_cols":10,"rows_kept":23,"flags":["formulas_cached_only"]}
[null,null,"due","JPL","U. Col.","Brown","Indiana","UCI","USC","Total Value ($K)"]
["Administration"]
["A","Software engineering plan completed","2002-03-01",19,15,15,15,5,15,84]
["B","First Annual Report delivered ","2003-01-30",60,{"$nulls":5},60]
["C","Second Annual Report delivered","2004-01-30",60,{"$nulls":5},60]
["D","Final Report delivered","2004-08-30",50,{"$nulls":5},50]
["Code Improvement"]
[]
["E","Code Baselines, Scaling Analysis, Performance Analysis completed  (generate scaling curves for codes which are already parallel, baseline serial performance for codes which are not already parallel)","2002-06-30",120,55,25,{"$nulls":3},200]
["F","First code improvement (Choose several from list below for functional enhancement and speedup)","2003-06-30",240,70,50,{"$nulls":3},360]
["G","2nd code improvement - further optimization for some codes, pick up others that were neglected in 1st improvement","2004-06-30",240,120,50,{"$nulls":3},410]
["Interoperability"]
["H","Review board approves requirements and a preliminary design for functionality.","2002-06-30",56,3,3,110,23,108,303]
["I","Review board approves ","2003-06-30",104,null,null,125,67,null,296]
["J","Review board approves delivery of completed framework and updated documentation for:","2004-06-30",70,30,null,125,42,null,267]
["K","Demonstrate integration of one external user application into the framework using the GRID framework wizards","2004-06-30",12,null,null,3,null,null,15]
["L","Issue testable 5 year earthquake forecast for M>5 for S California","2004-06-30",null,10,{"$nulls":4},10]
["Optional"]
["Funds are for non-in-house effort related to the in-house optional milestones","Riva: Produce movies of the strain, stress, and displacement  data generated from Virtual California and GeoFEST of 1 km resolution for S. California in an integrated way through the grid framework.","2003-06-30",13,10,null,5,null,null,28]
[null,"ParVox: Provide an interactive volumetric visualization tool to permit user-controlled view from arbitrary vantage points inside a volume, displaying 3D structure, strain, physical properties, meshes, and seismicity through the grid framework.","2004-01-30",5,{"$nulls":5},5]
[null,"PYRAMID: Mesh generation - Demonstrate adaptive mesh capability within GeoFEST using a fault stepover geometry wherein the mesh is adapted to accommodate large strain gradients in the stepover as the displacement on the main faults grows, and coarsening of the mesh in areas wherein the strain field grows smoother.","2004-06-30",60,{"$nulls":5},60]
[]
["TOTAL",null,null,1109,313,143,383,137,123,2208]