# Software Engineering / Development Plan

- Introduction

  - Purpose

## Brief statement of the project’s purpose

- We plan to develop a solid earth system science framework for creating an understanding of active tectonic and earthquake processes.

  - Background

Brief description that shows where the software products produced by the project fit into the overall system

This project will create an overall system. Many of the individual components already exist in some form (see code descriptions) and will be parallelized to allow us to address larger problems and wrapped as objects to be brought into an integrated problem solving environment PSE. The PSE will be built using these components and the Gateway and Community Grids Collaboratory also described in the code descriptions.

  - Organization and Responsibilities

    - Project Personnel

Explanation of how the development team will organize activities and personnel to carry out the project; types and numbers of personnel assigned; team members’ authorities and responsibilities.

The development team is composed of a group of collaborators distributed across the US at various institutions. Each group has a well defined part of the project in which they have recognized cognizance and authority which derives from the fact that they are contributing a significant module and expertise that they have already spent considerable effort developing.

Dr. Andrea Donnellan is the PI of this project and will oversee all aspects of the work. Many of the team members have worked extensively and effectively together in the past. We recognize that managing such a large team can be difficult. We therefore plan to conduct regular reviews during the course of this work. We will also hold meetings at JPL in which all of the team members can interact and plan work. Team members will be responsible for developing and completing different components of the system as outlined in the following table in which we itemize the components of the system, the responsible members and their background and skills relating to that component of the framework.

| ###### Component | ###### Team Members | ###### Task, Background, and Skills |
| --- | --- | --- |
| Database system | Dennis McLeod Lisa Grant Andrea Donnellan | Database systems Geology/paleoseismology Tectonics, earthquakes |
| Finite element code | Greg Lyzenga Jay Parker John Lou | Parallel computation/FEM Parallel computation/FEM Parallel computation/FEM/AMR |
| Inversion and assimilation codes | Greg Lyzenga John Rundle Terry Tullis John Lou | Inversion Viscoelastic models Fault nucleation, fast multipoles Fast multipoles, data assimilation |
| Object broker | Geoffrey Fox Dennis McLeod | Science interoperability Science interoperability |
| Visualization codes | Geoffrey Fox Andrea Donnellan | Visualization and integration in portals Geophysical applications |
| Pattern recognizers | Robert Granat John Rundle | Hidden Markov Modeling Pattern dynamics |
| Disaster management system | Andrea Donnellan Jay Parker Greg Lyzenga Geoffrey Fox Jill Andrews | Earthquakes, data interpretation Data integration Modeling Software Integration Interfacing with customers |
| Outreach | Jill Andrews | Outreach to earthquake community |

    - Interfacing Groups

### List of interfacing groups and points of contact

| ###### Component | ###### Institution | ###### Person | ###### Phone | ###### Email |
| --- | --- | --- | --- | --- |
| Database system | USC UCI JPL | Dennis McLeod Lisa Grant Andrea Donnellan | 818-354-4737 | Andrea.Donnellan@jpl.nasa.gov |
| Finite element code | JPL JPL JPL | Greg Lyzenga Jay Parker John Lou | 818-354-6920 818-354-6790 818-354-1146 | Gregory.A.Lyzenga@jpl.nasa.gov Jay.W.Parker@jpl.nasa.gov John.Z.Lou@jpl.nasa.gov |
| Inversion and assimilation codes | JPL U Colo Brown U JPL | Greg Lyzenga John Rundle Terry Tullis John Lou | See above | See above |
| Object broker | Indiana U USC | Geoffrey Fox Dennis McLeod |  |  |
| Visualization codes | Indiana U JPL | Geoffrey Fox Andrea Donnellan | See above | See above |
| Pattern recognizers | JPL U Colo | Robert Granat John Rundle | 818-393-5353 | Robert.A.Granat@jpl.nasa.gov |
| Disaster management system | JPL JPL JPL Indiana U Caltech | Andrea Donnellan Jay Parker Greg Lyzenga Geoffrey Fox Jill Andrews | See above See above See above | See above See above See above |
| Outreach | Caltech | Jill Andrews |  |  |
| Configuration and overall Software engineering | JPL | Ken Hurst | 818-354-6637 | Kenneth.Hurst@jpl.nasa.gov |
| Overall Management | JPL | Andrea Donnellan | See above | See above |

- Statement of the Problem

Brief elaboration of the requirements, the steps to be taken to accomplish the project and the relation (if any) to other projects

We are building a new Problem Solving Environment for use by the seismological and tectonics communities.

Our objective is to develop a system with the following specific components.

- A database system for handling both real and simulated data.

- Fully three-dimensional finite element code with adaptive mesh generator capable of running on workstations and supercomputers for carrying out earthquake simulations.

- Inversion algorithms and assimilation codes for constraining the models and simulations with data.

- A collaborative portal (object broker) for allowing for seamless communication between codes, reference models, and data.

- Visualization codes for interpretation of data and models.

- Pattern recognizers capable of running on workstations and supercomputers for analyzing data and simulations.

- Disaster management system for response and analysis following earthquakes.

At the top-level operational architecture of our proposed solid earth system science framework system science users interact with interface programs as well as modeling, simulation, and analysis tools. These programs generate requests for data in XML/SQL form, issuing them to a distributed object broker constructed in CORBA or Java. This broker dispatches requests to structured databases, managed by a general-purpose database management system, as well as to files and web-based data sources; the latter will be wrapped using mediator technology to look like structured databases. Data integration mechanisms are then employed to fuse data from multiple sources. Information is then returned through the broker to the requestor, in XML form.

One of the most critical aspects of our proposed system is supporting interoperability given the heterogeneous nature of data sources as well as the variety of application programs, tools, and simulation packages that must operate with data from our system. Interoperability will be implemented by using distributed object technology combined with development of object API's that conform with emerging standards. We will define our object API's in XML and dynamically map this specification into the chosen object model. This strategy was successfully used in the Gateway portal, which currently uses a CORBA middle tier but has used a pure Java solution with the same objects.

SCEC ITR

- Technical Approach

  - Assumption and constraints

  - Development environment

Hardware platform(s) and programming language(s)

  - Activities, tools and products (including documentation)

Activities to be performed; design methodology and tools to be applied; products generated – including documentation

Address software development phases:

Requirements analysis (*)

Preliminary/detailed design  (*)

Testing  (*)

Maintenance  (*)

  - Build strategy

Which portions of the system will be built/delivered in each phase of the project

- Management Approach

  - Assumptions and constraints

  - Milestones and Schedules

| Milestone | Expected completion date | Value |
| --- | --- | --- |
| Administration |  |  |
| A) Software engineering plan completed Deliver software engineering plan describing software engineering infrastructure within the Investigator Team. | 6/30/01 | $104K |
| B) First Annual Report delivered Prepare and deliver first annual report to ESS via Web. | 1/30/02 | $120K |
| C) Second Annual Report delivered Second annual report submitted to ESS via Web. | 1/30/03 | $120K |
| D) Final Report delivered Final Report submitted to ESS via Web. | 1/30/04 | $55K |
| Code Improvement |  |  |
| E) Code baseline completed Code baseline completed: demonstrate parallel operation and scaling for Multipole fault-patch, finite element codes. (Other codes are part of later interoperable demonstration suite, so not part of this benchmark). Demonstrate both at 1 km surface resolution, the first demonstrating Parkfield nucleation, the second Northridge postseismic relaxation. Baseline parallel HMM code implemented. Demonstrate scaling and functionality using seismic records. Baseline 3D FEM code on a Northridge class event. | 6/30/01 | $206K |
| F) First code improvement completed Improve Multipole and finite element codes, at under 500 m surface resolution. For Multipole code demonstrate multiple fault interaction (triggering on a disconnected fault from first event), toward full Virtual California implementation. For Finite Element code, also show multiple-fault interaction case with use of automatic parallel mesh refinement. First code improvement implemented. Improve computational efficiency through improved algorithm and numerical implementation. Add functionality: method will automatically determine the optimal number of classes. Test functionality and efficiency using seismic records, fused GPS data. | 6/30/02 | $305K |
| G) second code improvement completed Improve codes to demonstrate maximum-sized in-core solution on a leading NASA testbed. Adapt Multipole code to Virtual California (viscoelastic layer Greens function) physics and detailed fault-model test case. Relax resolution to 1 km at surface, but run full fault system for 10,000 years. For Finite Element code, demonstrate 1000 year simulation of realistic Southern California fault system, including layered rheology and diverse fault types. Demonstrate scaling of each to full machine capacity. Second code improvement implemented. Add functionality: method will perform automatic feature selection and dimension reduction. Method will also plug into a real-time system to test predictive capability. | 6/30/04 | $420K |
| Interoperability |  |  |
| H) Design policy for interoperability and community delivery agreed on Agree on distributed object essential structure: contact points, initial technologies and standards, mechanism for potential users to gain access, wrapperize codes, register resources. | 6/30/01 | $290K |
| I) Interoperability prototype tested with improved codes Demonstrate invocation of improved milestone "F" codes through prototype portal using distributed web method. | 6/30/02 | $430K |
| J) Full interoperability demonstrated using improved codes Full-fledged web-object infrastructure demonstration, with browser-based portal. Post infrastructure details, documentation, and source on Web. Post working examples invoking chain of operations including Multipole code and Finite Element code together with flow of science data from web-based databases and display of results with intuitive visualization tools. | 6/30/03 | $430K |
| K) Customer delivery accomplished Customer delivery - deliver simulation codes, portal, and components to 5 research groups associated with the Southern California Earthquake Center and/or the APEC Cooperation for Earthquake Simulations. Likely candidates include USC, UC Davis, USGS, UCSD, MIT, SCEC, other JPL groups, GSFC. | 11/30/03 | $95K |
| L) Software tools completed | 11/30/03 | $85K |
| ### Education and Public Outreach |  |  |
| M) Partnerships formed Two workshops held with educational advisors, Web authors and E-Cube partners from SCEC, IRIS and JPL to establish workplan, tasks, Web design, pedagogy and topical content for educational tools development. Two workshops held to identify partners among Federal, state, local, and regional emergency managers interested in earthquake forecasting tools based on computational models; and to develop a workplan with related tasks for transfer. Partnership agreements established. | 1/30/02 | $30K |
| N) Educational tools completed Content for Web-based module and E-Cube produced and submitted for review. Educational tools (Web-based module and E-CUBE content) completed and announced via WWW. | 11/30/02 | $55K |
| O) Disaster tools developed and transferred Version 1.0, earthquake forecasting tool for disaster managers completed and submitted to partners for beta-testing and feedback. Disaster tools transferred. | 11/30/02 | $50K |

  - Metrics

Identify which measures will be collected to capture project data

  - Risk Management

Identify the technical and managerial risks or concerns and how they will be mitigated

- Product Assurance

  - Configuration Management  (*)

Identify person responsible for CM and describe his role.

Identify products (software baselines and documentation) that will be under CM control.

Identify procedures and tools that will be used to implement CM

  - Quality Assurance  (*)

Identify person responsible for QA and describe his role.

Identify procedures and products that will be subject to QA.

Identify QA reports resulting from QA activities

(*)  --  May require separate document